## OpAMP_Capabilities_Roadmap
Capability Group | Capability | Description | Status | Priority | Effort (Phase 1) | Comments
Core Platform | OpAMP Server Cluster (AWS) | A multi-region, active-active cluster of servers that form the control plane. | Planned | P0 | High | Requires infrastructure setup in AWS (EKS, RDS, etc.) and high-availability design.
Core Platform | Supervisor Proxy (Linux | Win | macOS) | A lightweight proxy (< 50 MB RAM) that runs on each endpoint as a single OpAMP client. | Planned | P0 | High | Requires building and packaging for all three major operating systems.
Agent Inventory | Automatic Registration | Agents automatically register with the OpAMP server on first boot. | Planned | P0 | Low | A simple bootstrap process using a one-time token.
Agent Inventory | Dynamic Fleet Inventory | A real-time, searchable inventory of all agents, their versions, and their status. | Planned | P0 | Medium | Requires a database (e.g., RDS) to store and query agent metadata.
Configuration | Centralized Push Updates | The ability to push configuration changes to the entire fleet in near real-time. | Planned | P0 | Medium | The core of the OpAMP protocol; requires robust WebSocket handling.
Configuration | Git-Based Versioning | All configurations are stored in a Git repository, providing versioning, auditing, and rollback. | Planned | P0 | Medium | Integrates with existing CI/CD pipelines for configuration management.
Health Monitoring | Continuous Health Checks | The supervisor continuously monitors the health of each managed agent. | Planned | P1 | Medium | Health checks include CPU, memory, and restart counts.
Health Monitoring | Real-Time Metrics & Dashboards | A centralized dashboard showing the health and performance of the entire agent fleet. | Planned | P1 | High | Requires a time-series database (e.g., Prometheus) and a visualization tool (e.g., Grafana).
Package Management | Remote Updates & Upgrades | The ability to remotely update and upgrade agent binaries. | Planned | P1 | High | A critical feature for maintaining security and delivering new features.
Package Management | Artifactory Integration | Agent binaries are stored in Artifactory, providing a secure and reliable distribution point. | Planned | P1 | Medium | Integrates with existing Artifactory infrastructure.
Deployment Strategies | Canary Deployments | The ability to roll out changes to a small subset of the fleet before a full rollout. | Planned | P1 | High | A key feature for reducing deployment risk.
Deployment Strategies | Tag-Based Targeting | The ability to target deployments to specific groups of endpoints based on tags (e.g., region, OS). | Planned | P1 | Medium | Requires integration with a tag management system.
Deployment Strategies | Instant Rollback | The ability to instantly roll back a failed deployment. | Planned | P1 | Medium | A critical feature for maintaining service availability.
Security & Compliance | mTLS Authentication | All communication between the supervisor and the OpAMP server is authenticated using mutual TLS. | Planned | P2 | Medium | Requires a PKI infrastructure for issuing and managing certificates.
Security & Compliance | RBAC & Audit Trail | Role-based access control and a complete audit trail for all changes. | Planned | P2 | Medium | Ensures that only authorized users can make changes and that all changes are tracked.
Agent Wrappers | CrowdStrike Falcon/LogScale | A wrapper that allows the supervisor to manage CrowdStrike agents. | Planned | P2 | Medium | Requires reverse-engineering the CrowdStrike agent's configuration and management APIs.